## Slide 1: Automated spatiotemoral annotation of sound oject in a scene
Einari VAARAS
Kalle LAHTINEN
Mehmet AYDIN
COMP.SGN.250 Signal Processing Innovation Project
Project Plan Report

## Slide 2: Abstract

## Slide 3: Project background
This project is the course work for a Tampere University course ’Signal Processing Innnovation Project’ designed for students majoring in signal processing and machine learning.
The course will be completed during spring of the year 2021.
the project will be carried out by Kalle Lahtinen, Einari Vaaras and Mehmet Aydin

## Slide 4: Project organization
1. Project Members
The Project members are Einari Vaaras, Mehmet Aydin and Kalle Lahtinen
There are no specific roles defined for the members
Discussions about the project are held on telegram-channel
the aim of the project is for each group member to contribute to the project and learn something new.

## Slide 5: Project organization
2. Clients
This Project will be supervised by Archontis Politis and Tuomas Virtanen working at the Audio Research Gruop at Tampere University

## Slide 6: Project Objectives
  The Project objectives are divided into two categories as follows,
  Basic goals
  Advance Goals
  The separate goals are planned to make sure at least the minimal wanted result for the project is achieved

## Slide 7: Project Objectives
  Basic Goals
  The basic goal is to achieve the minimal wanted results for the Project.
  Each Project member aims to gain 5 credits for the project work.
  The work spent on the basic goal will be about 133.3 hours for each Project member.

## Slide 8: Project Objectives
  Basic Goals
  The objectives of the basic goal are as follows:
  Project initialization and planning
  Studying object detetction methods for 360-degree video data
  Working on the open source code to get familiar on how object tracking methods could be applied to the Project.
  determining and defining the scenes to be recorded

## Slide 9: Project Objectives
  Basic Goals Cont.
  Extracting temporal object detections and their locations from the video recording
  Formulating spatiotemporal labels for the audiodata by combining video and audio detetctions
  Testing the method against manual annotation

## Slide 10: Project Objectives
  Advance Goals
  Kalle will take care

## Slide 11: References
[1] N.S. Punn, S.K. Sonbhadra, S. Agarwal ‘Monitoring COVID-19 social distancing with person detetction and tracking via fine-tuned YOLOv3 and deep-sort techniques.’
[2] J.P. Queralta, J. Taipalmaa, B.C. Pullinen, V.K. Sarker, T.N. Gia, H. Tenhunen, M. Gabbouj,J. Raitharju, T. Westerlund ‘Collaborative Multi-Robot Search and Rescue: Planning, Coordination, Perception and Active Vision’
[3] T.W Mi, M.T Yang ‘Comparison of Tracking Techniques on 360-Degree Videos’, 2019
.